# Event-Based Surveillance (EBS) Training of Trainers – Planning Checklist

This document is to support the planning and implementation of an EBS Training of Trainers (ToT).

## ToT Goal and Expected Outcome

The EBS ToT and toolkit can be used to both sensitize and train national and subnational surveillance staff on event-based surveillance. The goal is to strengthen national EBS capacity by training master trainers on EBS principles and practices (Week 1) and co-developing cascaded training materials and implementation tools such as Standard Operating Procedures (SOPs), signal lists, reporting templates, and job aids (Week 2).

For best results, national surveillance leadership should be sensitized and supportive of this activity and participants should include: national and sub-national surveillance staff, EBS focal points, training institution representatives, informaticians, and monitoring and evaluation specialists that support the EBS surveillance program.

Outcomes include a cadre of EBS trainers, a country-adapted EBS training package, and draft implementation materials ready for national and sub-national rollout.

## Key Roles

| Role | Responsibilities |
| --- | --- |
| Core Planning Team (e.g. National Ministry of Health (MoH), US CDC, partners) | Overall coordination, funding, agenda approval |
| Training Leads/Facilitators | Curriculum finalization, facilitation during Week 1, mentoring and facilitation during Week 2 |
| Logistics Lead | Venue, travel, lodging, materials, translation |
| Technical Working Group | Drafting SOP/guidance, signal list, adaptation of slides/manuals |

## TOT Planning and Implementation Team

| Role | Name | Organization | Contact-email | Contact- phone |
| --- | --- | --- | --- | --- |
| Core Planning Team |  |  |  |  |
| Training Leads/Facilitators |  |  |  |  |
| Logistics Lead(s) |  |  |  |  |
| Technical Working Group |  |  |  |  |

## Dates and Venue:

- Confirmed ToT dates: (TBD – 2 weeks)

  - Preparation day:

  - Training: week 1

  - ToT Adaptation: week 2

- Venue: (ADD name, location, address)

## Planning Timeline and Action Items

Expected Communication: Weekly planning calls, shared online workspace for documents, single email list for all partners.

Recommended lead time: minimum 60 days before Week 1 start date. The following are the minimum activities required to prepare for in advance of an EBS ToT. However, additional activities may be required as trainings are customized in order to meet a country’s needs.

| Action Item | Responsible Party | Target Date |  | Notes |
| --- | --- | --- | --- | --- |
| Establish Core Planning Team and designate primary/alternate Points of Contact (POCs) | National MoH + partners | D-60 |  | Include surveillance, training, and logistics representatives |
| Determine modules to be covered in the ToT and identify training leads and facilitators | Core Team | D-55 |  |  |
| Confirm funding sources (venue, participant travel, per diem, materials, translation/interpretation) | Core Team | D-55 |  | Identify gaps and partner contributions |
| Finalize dates & secure venue for 2-week training | Logistics Lead | D-55 |  | Ensure space for plenary + breakout sessions |
| Develop/agree on participant selection criteria (national surveillance staff, sub-national trainers) | Core Team | D-50 |  | Target ~25 participants for Week 1 |
| Review and adapt EBS core training curriculum | Training Leads/Facilitators | D-45 |  | Pre-load with country examples and current SOPs |
| Prepare and share draft templates with the Technical Working Group (signal list, SOPs, reporting forms) | Training Leads/Facilitators | D-40 |  | Will be refined during Week 2 |
| Arrange translation/interpretation if needed | Logistics Lead | D-40 |  | Translate slides, manuals, job aids |
| Send “Save-the-Date” and invitation letters | Core Team | D-40 |  | Include agenda overview and participant expectations |
| Finalize detailed agenda for Week 1 (training) and Week 2 (materials adaptation) | Training Leads/Facilitators |  | D-30 | Identify facilitators for each module |  |
| Conduct planning calls/meetings (weekly) | Core Team |  | D-30 onward | Track logistics, curriculum, and participant confirmations |  |
| Finalize training materials, handouts, evaluation tools | Training Leads/Facilitators |  | D-14 | Print or load to USB/cloud |  |
| Confirm travel and lodging arrangements | Logistics Lead |  | D-10 | Ensure arrival prior to Day 1 |  |
| Hold EBS ToT – Week 1: Training | All |  | Day 1–5 | Core EBS concepts, exercises, assessments |  |
| Hold EBS ToT – Week 2: Adaptation & Implementation | All |  | Day 6–10 | Revise training package, draft SOPs, finalize signal list |  |
| Compile final training package & implementation toolkit | Training Leads/Facilitators + Technical Working Group |  | End of Week 2 | Circulate for clearance |  |
| Post-training evaluation and follow-up plan | Core Team + Technical Working Group |  | +2 weeks | Include schedule for cascaded trainings |  |